## investmenter app
InvestMenter App
Panning
Name | Status | Priority | Platform | Owner | Due Date | Notes
Define App Requirements & Scope | Done | Critical | Both |  |  | Document all features and user stories
Create Wireframes & UI Mockups | Done | High | Both |  |  | Mobile-first design approach
Technical Architecture Design | Done | High | Both |  |  | Frontend/Backend/Database structure
Sprint Planning & Timeline | Done | High | Both |  |  | Define milestones and deadlines
Resource Allocation | Done | Medium | Both |  |  | Assign team members to tasks
Risk Assessment | Done | Medium | Both |  |  | Identify potential blockers
Budget Planning | Done | Medium | Both |  |  | Development and deployment costs
Infrastructure and Deployment
Name | Status | Priority | Platform | Owner | Due Date | Notes
Frontend Firebase Deployment | Done | High | Both |  |  | Firebase Hosting configured
Backend Google Cloud Deployment | Done | High | Both |  |  | GCP Cloud Run deployed
Firebase Database Setup | Done | High | Both |  |  | Firestore configured
Firebase Authentication | Done | High | Both |  |  | Email/Password auth enabled
Core Features
Name | Status | Priority | Platform | Owner | Due Date | Notes
User Authentication Flow | Done | High | Both |  |  | Login/Register/Password Reset
Dashboard View | Done | High | Both |  |  | Portfolio overview with welcome header
Portfolio Section | Done | High | Both |  |  | Investment tracking and totals
Properties View | Done | High | Both |  |  | PropertyView component
Document Management | Done | High | Both |  |  | Upload view AI extraction
Payment Tracking | Not Started | Medium | Both |  |  | Payment history and schedules
Profile Management | Done | Medium | Both |  |  | User profile editing
Mobile-Specific Features
Name | Status | Priority | Platform | Owner | Due Date | Notes
Bottom Navigation Bar | Done | High | Both |  |  | 5-tab DEWA-style navigation
Mobile Header Component | Done | High | Both |  |  | Search and profile icons
Responsive Sidebar | Done | High | Both |  |  | Desktop collapse mobile slide-in
Touch Gestures | Done | Medium | Both |  |  | Swipe pull-to-refresh
Push Notifications | Done | Medium | Both |  |  | Firebase Cloud Messaging
Offline Mode / Caching | Not Started | Low | Both |  |  | Service worker setup
App Icon & Splash Screen | Done | Medium | Both |  |  | Branded assets needed
AI & Advanced Features
Name | Status | Priority | Platform | Owner | Due Date | Notes
AI Chatbot Integration | Done | High | Both |  |  | ChatbotView component
Document AI Extraction | Done | Medium | Both |  |  | Auto-extract from uploads
Cashflow Calculator | Done | Medium | Both |  |  | CashflowCalculator component
Roi Calculator | Done | Medium | Both |  |  | Statement of Account
Portfolio Analysis Charts | Done | Medium | Both |  |  | Visual analytics
Content & Community
Name | Status | Priority | Platform | Owner | Due Date | Notes
Events Section | Done | Medium | Both |  |  | Investor events listing
Webinar Section | Done | Medium | Both |  |  | Video/webinar access
News Feed | Done | Medium | Both |  |  | Real estate news
IM Properties Listing | Done | Medium | Both |  |  | InvestMenter properties
Marketplace/Services | Done | Medium | Both |  |  | Visa legal sales services
Experience Section | Done | Low | Both |  |  | VIP experiences
WhatsApp Community Links | Done | Low | Both |  |  | Developer community channels configured
Backend & API Integration
Name | Status | Priority | Platform | Owner | Due Date | Notes
Close CRM Integration | Done | High | Backend |  |  | closeCrmService.js
CRM Sync Service | Done | High | Backend |  |  | crmSync.js
Google Drive API | Done | Medium | Backend |  |  | Document storage
Cashflow Routes API | Done | Medium | Backend |  |  | cashflowRoutes.js
User Data Endpoints | Done | High | Backend |  |  | Units payments documents
Error Handling & Logging | In Progress | Medium | Backend |  |  | logs.txt monitoring
Testing & QA
Name | Status | Priority | Platform | Owner | Due Date | Notes
Unit Testing Setup | Not Started | Medium | Both |  |  | Jest/React Testing Library
API Integration Tests | Not Started | Medium | Backend |  |  | Endpoint testing
Mobile Responsiveness Testing | Not Started | High | Both |  |  | Multiple device sizes
Cross-browser Testing | Not Started | Medium | Web |  |  | Chrome Safari Firefox
iOS Device Testing | Not Started | High | iOS |  |  | iPhone models
Android Device Testing | Not Started | High | Android |  |  | Various manufacturers
User Acceptance Testing | Not Started | High | Both |  |  | Stakeholder review
Apple Developer Account | Not Started | High | iOS |  | ,$99/year enrollment
Google Play Developer Account | Not Started | High | Android |  | ,$25 one-time
App Store Screenshots | Not Started | Medium | Both |  |  | Marketing assets
App Description & Keywords | Not Started | Medium | Both |  |  | ASO optimization
Privacy Policy Page | Not Started | High | Both |  |  | Required for stores
Terms of Service | Not Started | High | Both |  |  | Legal requirements
App Store Review Submission | Not Started | High | iOS |  |  | Apple review process
Google Play Submission | Not Started | High | Android |  |  | Google review process
App Store Preparation
Name | Status | Priority | Platform | Owner | Due Date | Notes
Milestones & Releases
Name | Status | Priority | Platform | Owner | Due Date | Notes
Alpha Release - Internal | Not Started | Critical | Both |  |  | Core features working
Beta Release - Investors | Not Started | Critical | Both |  |  | Selected user testing
v1.0 Production Release | Not Started | Critical | Both |  |  | Full public launch
v1.1 Feature Update | Not Started | High | Both |  |  | Post-launch improvements